## PRODUCT BACKLOG
E- COMMERCE PRODUCT BACKLOG
Sn. No. | USER | PRIORITY | USER STORY | SCRUM ASSIGNED TEAM | ACCEPTANCE Testing | STATUS | REMARK
SPRINT 1
1 | user01 | High | User Registeration | Member 1 | YES | COMPLETED
2 |  | Medium | Login page | Member 2 |  | COMPLETED
SPRINT 2
3 | user02 | High | User Dashboard | Member 2 | Yes | PLANNING
4 |  | High | Admin Dashboard | Member 3 | No
SPRINT 3
5 | user03 | High | Buying | Member 2 | Yes | TESTING GOING ON
6 |  | low | Cart | Member 4 | Yes | TESTING GOING ON
7 |  | Medium | Order List | Member 5 | Yes | TESTING GOING ON
8 |  | medium | Order Cancel | Member 2 | Yes | TESTING GOING ON
SPRINT 4
9 | user04 | High | Selling | Member 1 | Yes | DESIGINING
10 |  | Medium | Track order | Member 2 | Yes
SPRINT 5
11 | user05 | High | Customer Chat Support | Member 1 | Yes | COMPLETED
12 |  | High | Customer Call Support | Member 2 | Yes | COMPLETED
13 |  | medium | Feedback | Member 3 | Yes | PROGRESS
14 |  | medium | Notification | Member 4 | Yes | PROGRESS
15 |  | medium | Review and Rating product | Member 5 | Yes | PROGRESS

## SPRINT 1
Sn no. | USER | USER STORY | USER STORY DEFINITION |  |  | ESTIMATED TIME | ACTUAL TIME | ASSIGNED TO | STATUS
| User01 |  | AS A | I WANT TO | SO THAT I CAN
1 |  | User Registeration | As User | I can be able to Regiter myself for first time | I can able to login | 2 Days | 1.5 Day | Member 1 | COMPLETED
2 |  | Login Page | As User | I can be able to Login Myself | I can able to View User Dashboard | 1 Day | 15 hours | Member 2 | COMPLETED
3 |  | Login Page | As Admin | I can be Able Login Myself | I can be able to view Admin Dashboard

## SPRINT 2
Sn no. | USER | USER STORY | USER STORY DEFINITION |  |  | ESTIMATED TIME | ACTUAL TIME | ASSIGNED TO | STATUS
|  |  | AS A | I WANT TO | SO THAT I CAN
1 | User02 | User Dashboard | As a USER | I can be able to view products | I can order | 3 Days | 4 Days | Member 2 | PLANNING
2 |  |  | As a USER | I can be able to search the product | I Can get the list
3 |  |  | As a USER | I can be able to Select the Category | I can get my desired Product type
4 |  |  | As a USER | I can be able to view MY PROFILE | I can view my Information
5 |  | Admin Dashboard | As a ADMIN | I can be able to Contorl panel | I can get control over buyer and seller | 5 Days | 4 Days | Member 3 | PLANNING
6 |  |  | As a ADMIN | I can be able to Control product Listing. | I can view Product details
7 |  |  | As a ADMIN | I can be able to Track BUYING | I can get report of no. of item purchased
8 |  |  | As a ADMIN | I can be able to track Selling | I Can get report of no. item Sold.

## SPRINT 3
Sn no. | USER | USER STORY | USER STORY DEFINITION |  |  | ESTIMATED TIME | ACTUAL TIME | ASSIGNED TO | STATUS
|  |  | AS A | I WANT TO | SO THAT I CAN
1 | User03 | Buying | AS A User | I can be able to BUY | I Can purchase the product | 5 hours | 9 hours | Member 2
2 |  | Cart | AS A User | I can be able to Use Cart | I Can get the product inside Cart | 6 hours | 4 hours | Member 4
3 |  | Order List | AS A User | I can be able to See the List of past order | I Can get see my orders | 10 hours | 12 hours | Member 5
4 |  | Order Cancel | AS A User | I can be able to Cancel | I Can Cancel if wrong item is placed | 5 hours | 5 hours | Member 2

## DEFECT SHEET
Defect ID | Defect | Created on | Creator | Assigned | Priority | Status
1001 | Unable to Select the Category | 2024-06-07 | Sangita | neha | medium | open
1002 | Unable to ADD item in cart | 2024-06-08 | pooja | shiv | high | open
1003 | unable to select debit card in paymnet | 2024-06-09 | rutuja | shree | high | open
1004 | Order tracking fail | 2024-06-10 | prandya | neha | high | closed
1005 | Coupon Code Application | 2024-06-11 | prince | shiv | low | closed
LOGIN PAGE
USERNAME
PASSWORD
USER DASHBOARD
BUTTON
HOME
PRODUCT CATEGORY
SEARCH HOME CATEGORY